{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["甘特图"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"甘特图","index":0,"n_rows":39,"n_cols":10,"rows_kept":39,"cut":false,"hidden":false,"merged":[[6,0,35,0],[6,1,9,1],[10,1,35,1],[6,2,9,2],[10,2,11,2],[12,2,14,2],[15,2,16,2],[17,2,18,2],[19,2,21,2],[22,2,27,2],[28,2,32,2],[33,2,35,2],[6,4,9,4],[10,4,11,4],[12,4,14,4],[15,4,16,4],[17,4,18,4],[19,4,21,4],[22,4,27,4],[28,4,32,4],[33,4,35,4],[0,0,3,9]]}
["小炒项目计划表\nproject plan"]
[]
[]
[]
["平均进度：",{"$f":"AVERAGE(I7:I36)","v":0},null,"已完成：",{"$f":"COUNTIF(I7:I37,100%)","v":0},"待完成：",{"$f":"COUNTA(D7:D36)-E5","v":30}]
["实施阶段","模块",null,"任务计划内容","人员","开始日","预计工期","结束日","完成比例","完成情况"]
["内部研发\n","云端管理系统","*","云端管理系统商品信息","赵样","2023-06-26",null,"2023-06-30",0,"执行中"]
[null,null,null,"云端管理物料位置信息",null,"2023-06-26",null,"2023-06-30",0,"执行中"]
[null,null,null,"云端管理工序模型、商品工序工艺信息",null,"2023-06-26",null,"2023-06-30",0,"执行中"]
[null,null,null,"云端提供接口获取云端菜谱、上传菜谱接口",null,"2023-06-26",null,"2023-06-30",0,"执行中"]
[null,"本地化控制系统\n【Android】","烹饪管理","菜品烹饪","奉友福","2023-06-24",null,"2023-06-30",0,"未开始"]
[null,null,null,"设备清洗",null,"2023-06-24",null,"2023-06-30",0,"未开始"]
[null,null,"菜谱管理","本地菜谱管理","奉友福","2023-06-24",null,"2023-06-30",0,"未开始"]
[null,null,null,"常用菜谱管理",null,"2023-06-24",null,"2023-06-30",0,"未开始"]
[null,null,null,"云端菜谱管理",null,"2023-06-24",null,"2023-06-30",0,"未开始"]
[null,null,"烹饪工序管理 ","工序信息管理","奉友福","2023-06-30",null,"2023-07-08",0,"未开始"]
[null,null,null,"工序模型管理",null,"2023-06-30",null,"2023-07-08",0,"未开始"]
[null,null,"菜谱信息&工艺管理","菜谱信息设置","奉友福","2023-06-30",null,"2023-07-08",0,"未开始"]
[null,null,null,"菜谱工艺步骤配置",null,"2023-06-30",null,"2023-07-08",0,"未开始"]
[null,null,"DIY管理","菜谱信息设置","奉友福","2023-06-30",null,"2023-07-08",0,"未开始"]
[null,null,null,"菜谱工艺配置",null,"2023-06-30",null,"2023-07-08",0,"未开始"]
[null,null,null,"手动操作模式自动记忆",null,"2023-06-30",null,"2023-07-08",0,"未开始"]
[null,null,"系统维护","主控PLC管理","奉友福","2023-07-08",null,"2023-07-22",0,"未开始"]
[null,null,null,"加热PLC管理",null,"2023-07-08",null,"2023-07-22",0,"未开始"]
[null,null,null,"辅料PLC管理",null,"2023-07-08",null,"2023-07-22",0,"未开始"]
[null,null,null,"投料PLC管理",null,"2023-07-08",null,"2023-07-22",0,"未开始"]
[null,null,null,"主投料PLC管理",null,"2023-07-08",null,"2023-07-22",0,"未开始"]
[null,null,null,"电机PLC管理",null,"2023-07-08",null,"2023-07-22",0,"未开始"]
[null,null,"系统设置","网络管理","奉友福","2023-07-08",null,"2023-07-22",0,"未开始"]
[null,null,null,"设备信息",null,"2023-07-08",null,"2023-07-22",0,"未开始"]
[null,null,null,"系统设置",null,"2023-07-08",null,"2023-07-22",0,"未开始"]
[null,null,null,"调料设置（液料校准、调料表、调料&泵管理信息）",null,"2023-07-08",null,"2023-07-22",0,"未开始"]
[null,null,null,"主控&加热管理",null,"2023-07-08",null,"2023-07-22",0,"未开始"]
[null,null,"数据采集与告警管理","调料缺料预警","奉友福","2023-07-08",null,"2023-07-22",0,"未开始"]
[null,null,null,"设备信息采集",null,"2023-07-08",null,"2023-07-22",0,"未开始"]
[null,null,null,"设备信息上报",null,"2023-07-08",null,"2023-07-22",0,"未开始"]
[]
[null,"一期功能"]
[null,"二期功能"]